## Project Planner
Nutrition Database Gantt Chart
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Inititating | 1 | 3 | 1 | 3 | 100%
1.1 Compile Project Team & Assign Project Manager | 1 | 2 | 1 | 2 | 100%
1.2 Identify & Meet with Stakeholders | 3 | 1 | 3 | 1 | 100%
2. Planning | 4 | 12 | 4 | 12 | 100%
2.1 Create Project Overview | 4 | 3 | 4 | 3 | 100%
2.2 Create Work Breakdown Structure (WBS) | 7 | 1 | 7 | 1 | 100%
2.3 Create Activity Definition Estimation | 8 | 2 | 8 | 2 | 100%
2.4 Create Gantt Chart | 10 | 2 | 10 | 2 | 100%
2.5 Determine System Vision | 12 | 1 | 12 | 1 | 100%
2.6 Collect & Determine Requirements & System Components | 13 | 1 | 13 | 1 | 100%
2.7 Create Software & User Interface Design | 14 | 2 | 14 | 2 | 100%
3. Executing | 16 | 16 | 16 | 16 | 100%
3.1 Create Food Search | 16 | 6 | 16 | 3 | 100%
3.2 Create Nutrition Breakdown | 16 | 6 | 16 | 5 | 100%
3.3 Create Nutrition Range Filter | 16 | 6 | 19 | 3 | 100%
3.4 Create Nutrition Level Filter | 22 | 6 | 24 | 3 | 100%
3.5 Create Meal Planner | 22 | 6 | 22 | 5 | 100%
3.6 Create User Interface | 22 | 6 | 22 | 2 | 100%
3.7 Final Testing | 28 | 4 | 27 | 5 | 100%
4. Controlling | 32 | 2 | 32 | 2 | 100%
4.1 Status Reports | 32 | 1 | 32 | 1 | 100%
4.2 Update Plans | 33 | 1 | 33 | 1 | 100%
5. Closing | 34 | 2 | 34 | 2 | 100%
5.1 Final Performance Review | 34 | 1 | 34 | 1 | 100%
5.2 Propose Final Report | 35 | 1 | 35 | 1 | 100%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%